## Görev Listesi
Task ID | Owner | Milestone | Task | Weight (0-100] | Start Date and Time | Completed Date and Time | URL | Details
1 | A. Safa Açıkgöz |  | Project repository editing and summary of the project document, reaching out to the team members. | 30 | 02.05.2026 12.00 | 04.05.2026 15.00 | https://github.com/safeapricot/se116-project/blob/main/README.md
2 | A. Safa Açıkgöz |  | Made a mind map to visualize the project | 50 | 04.05.2026 16.00 | 04.05.2026 17.10 | https://github.com/safeapricot/se116-project/blob/main/objectville%202%20mindmap.png
3 | Gökberk Gök |  | Designed the Core Object-Oriented Hierarchy and Package Structure. | 50 | 15.05.2026 14.00 | 15.05.2026 14.30
4 | Gökberk Gök |  | Implemented Concrete Models for Urban Grids | 60 | 15.05.2026 15.00 | 15.05.2026 16.30
5 | A. Safa Açıkgöz | file i/o | Started the File I/O | 50 | 16.05.2026 15.00 | 16.05.2026 18.30
6 | A. Safa Açıkgöz | file i/o | Finished the File input and cellGrid generation | 60 | 19.05.2026 14.00 | 19.05.2026 16.45
7 | A. Safa Açıkgöz | BFS search | Tried to understand the BFS search and added the isConnectable / added consumeUtility to Zone class / Made ResourcePool but deleted it after after understanding the logic | 60 | 19.05.2026 18.00 | 19.05.2026 21.00
8 | Ayberk ER |  | Zone class and consumeUtility | 60 | 23.05.2026 22.00 | 24.05.2026 00.00
9 | Ayberk ER |  | Housing,Industrial and Commerical classes and level and output calculations | 50 | 24.05.2026 17.00 | 24.05.2026 18.00
10 | Ayberk ER | providing services | The range and service type of services buildings | 30 | 24.05.2026 22.00 | 24.05.2026 23.00
11 | A. Safa Açıkgöz | BFS search | isConnectable mistakes resolved, added distributeBFS method and getNeighbors. Also added UtilityConsumer interface | 70 | 27.05.2026 18.00 | 28.05.2026 02.20
12 | A. Safa Açıkgöz | providing services | started the provideServices added setRadius to be completed tomorrow | 30 | 28.05.2026 03.00 | 28.05.2026 04.00
13 | A. Safa Açıkgöz | providing services | setRadius done // console output structure done | 40 | 28.05.2026 14.00 | 28.05.2026 15.30
14 | Ayberk ER | Overloading | The ResourcePool class was created, and spending methods (controlled by if/else statements) that prevent resource additions and negative balances were implemented in the code. | 70 | 28.05.2026 23.00 | 29.05.2026 01.30
15 | Arda Temel Birinci |  | Implemented ResourcePool, simulation loop, and fixed Zone calculations. | 80 | 28.05.2026 23.30 | 29.05.2026 04.00
16 | Arda Temel Birinci |  | Implemented terminal arguments and error handling for the ObjectVilleGame class. | 50 | 29.05.2026 05.00 | 29.05.2026 06.30
17 | Gökberk Gök |  | Implemented the distribution of utilities and resources. And update zones accordingly. | 70 | 30.05.2026 14.00 | 30.05.2026 15.20

## Developer List
Developer | Number of Tasks | Total Weight | Score | Team Average
Ahmed Safa Açıkgöz
Ayberk Er
Arda Temel Birinci
Ömer Gökberk Gök