## Görev Listesi
Task ID | Owner | Milestone | Task | Weight (0-100] | Start Date and Time | Completed Date and Time | URL | Details
1 | A. Safa Açıkgöz |  | Project repository editing and summary of the project document, reaching out to the team members. | 30 | 02.05.2026 12.00 | 04.05.2026 15.00 | https://github.com/safeapricot/se116-project/blob/main/README.md
2 | A. Safa Açıkgöz |  | Made a mind map to visualize the project | 50 | 04.05.2026 16.00 | 04.05.2026 17.10 | https://github.com/safeapricot/se116-project/blob/main/objectville%202%20mindmap.png
3 | Gökberk Gök |  | Designed the Core Object-Oriented Hierarchy and Package Structure. | 60 | 15.05.2026 14.00 | 15.05.2026 14.30
4 | Gökberk Gök |  | Implemented Concrete Models for Urban Grids | 70 | 15.05.2026 15.00 | 15.05.2026 16.30
5 | A. Safa Açıkgöz | file i/o | Started the File I/O | 50 | 16.05.2026 15.00 | 16.05.2026 18.30
6 | A. Safa Açıkgöz | file i/o | Finished the File input and cellGrid generation | 60 | 19.05.2026 14.00 | 19.05.2026 16.45
7 | A. Safa Açıkgöz | BFS search | Tried to understand the BFS search and added the isConnectable / added consumeUtility to Zone class / Made ResourcePool but deleted it after after understanding the logic | 60 | 19.05.2026 18.00 | 19.05.2026 21.00
8 | Ayberk ER |  | Zone class and consumeUtility | 60 | 23.05.2026 22.00 | 24.05.2026 00.00
9 | Ayberk ER |  | Housing,Industrial and Commerical classes and level and output calculations | 50 | 24.05.2026 17.00 | 24.05.2026 18.00
10 | Ayberk ER | providing services | The range and service type of services buildings | 30 | 24.05.2026 22.00 | 24.05.2026 23.00
11 | A. Safa Açıkgöz | BFS search | isConnectable mistakes resolved, added distributeBFS method and getNeighbors. Also added UtilityConsumer interface | 70 | 27.05.2026 18.00 | 28.05.2026 02.20
12 | A. Safa Açıkgöz | providing services | started the provideServices added setRadius to be completed tomorrow | 30 | 28.05.2026 03.00 | 28.05.2026 04.00
13 | A. Safa Açıkgöz | providing services | setRadius done // console output structure done | 40 | 28.05.2026 14.00 | 28.05.2026 15.30
14 | Ayberk ER | Overloading | The ResourcePool class was created, and spending methods (controlled by if/else statements) that prevent resource additions and negative balances were implemented in the code. | 70 | 28.05.2026 23.00 | 29.05.2026 01.30 |  | The commit problems I experienced on Git caused me to spend quite a while, which is why I was only able to push this commit to GitHub a day later.
15 | Arda Temel Birinci |  | Implemented ResourcePool, simulation loop, and fixed Zone calculations. | 90 | 28.05.2026 23.30 | 29.05.2026 04.00
16 | Arda Temel Birinci |  | Implemented terminal arguments and error handling for the ObjectVilleGame class. | 60 | 29.05.2026 05.00 | 29.05.2026 06.30
17 | Gökberk Gök |  | Implemented the distribution of utilities and resources. And update zones accordingly. | 70 | 30.05.2026 14.00 | 30.05.2026 15.20
18 | Ayberk ER | Bug fixing | Fixed UtilityType null pointer in Providers, corrected Euclidean distance formula, fixed ResourcePool consumption logic in distributeResources | 70 | 30.05.2026 21.00 | 31.05.2026 00.00
19 | Ayberk ER |  | Implemented UtilityConsumer interface and integrated it into the base Zone class. | 40 | 31.05.2026 02.00 | 31.05.2026 03.00
20 | A. Safa Açıkgöz | Bug fixing | Fixed the typos and some methods in SimulationManager, learned the jre file creation | 30 | 01.06.2026 11.00 | 01.06.2026 12.00
21 | A. Safa Açıkgöz | Output | added the manifest file, added the output system to a file that copies console output with System.setOut and made the logs file | 60 | 01.06.2026 12.30 | 01.06.2026 14.00 | https://www.tutorialspoint.com/java/lang/system_setout.htm | we were going to have a very bad time trying to change all the printLn's if we tried to use bufferedWriter, so i learned that there is a System.setOut method that copies all console output to a file. So i tried to implement that.
22 | Ayberk ER | BFS search | İmplemented total utility demand calculation and utility absorb via BFS, using polymorphism | 70 | 01.06.2026 20.00 | 01.06.2026 23.30
23 | Ayberk ER |  | Implemented the core game loop in SimulationManager and console output was formatted according to the desired sample output. | 80 | 03.06.2026 19.30 | 03.06.2026 22.00
24 | Ayberk ER |  | Leveling systems have been implemented for all zone classes d applied a consistent, iterative logic structure for level updates. | 50 | 03.06.2026 22.30 | 04.06.2026 00.00
25 | A. Safa Açıkgöz | Developer list | The Developer list page in Task point system automated with formulas in excel | 20 | 04.06.2026 00.00 | 04.06.2026 00.40
26 | Arda Temel Birinci |  | Refactored instanceof checks for code consistency, implemented InvalidMapException, and filled missing UtilityConsumer methods in Housing. | 50 | 04.06.2026 00.00 | 04.06.2026 01.00
27 | Arda Temel Birinci |  | Properly implemented and secured the Commercial class by adding safe map key (containsKey) checks for the Security service to prevent NullPointerException. | 90 | 03.06.2026 22.00 | 04.06.2026 02.00
28 | Arda Temel Birinci |  | Fixed map key typos (whitespace issues) and resolved multiple NullPointerException crashes in Housing class by securely integrating hasSecurity, hasHealth, and hasEducation checks. | 40 | 04.06.2026 00.30 | 04.06.2026 02.00
29 | Arda Temel Birinci |  | Refactored Zone subclasses by overriding toString() methods to ensure accurate object state logging instead of memory hash references. | 50 | 04.06.2026 02.00 | 04.06.2026 04.00
30 | Gökberk Gök |  | Fixed coordinate ordering and corrected getNeighbors to use the 8-cell neighborhood. | 60 | 04.06.2026 11.00 | 04.06.2026 11.50
31 | Gökberk Gök |  | Aligned console output with the reference output | 50 | 04.06.2026 12.00 | 04.06.2026 12.50
32 | Gökberk Gök |  | Prevented Industrial zones from consuming Internet only Housing and Commercial absorb Internet now, fixing utility distribution. | 60 | 04.06.2026 12.50 | 04.06.2026 13.40
33 | Gökberk Gök |  | Corrected zone level conditions: Industrial/Commercial require only Security for level-up; removed dead override methods from Housing. | 60 | 04.06.2026 14.00 | 04.06.2026 15.00
34 | Gökberk Gök |  | Fixed all the minor bugs and finalized the project | 80 | 04.06.2026 15.30 | 04.06.2026 17.00

## Developer List
Developer | Number of Tasks | Total Weight | Score | Team Average
A. Safa Açıkgöz | 11 | 500 | 100 | 477.5
Ayberk ER | 9 | 520 | 100
Arda Temel Birinci | 6 | 380 | 79.58
Gökberk Gök | 8 | 510 | 106.81